## Report
Test Case Report
Project Name | Daraz Online Shopping
Module Name | Sign Up and Sign In |  |  | Total No. | Status
Written By | Dhruba Nandi |  |  | 46 | PASS
Executed By | Dhruba Nandi |  |  | 3 | FAIL
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Total TC
| 46 | 3 | 49
Grand Total | 46 | 3 | 49

## TestCase
Product Name |  | https://www.daraz.com.bd/ | TC Start Date | DD--MM--YYYY | TC Execution Start Date | DD--MM--YYYY |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | DD--MM--YYYY | TC Execution End Date | DD--MM--YYYY |  | PASS | 46
| Test Exected BY: | Dhruba Nandi | [5 empty] | Fail | 3
[8 empty] | TOTAL | 49
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Final Status
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Mozilla Firefox Microsoft Edge | Passed
2 | User Management | UI Testing | Sign Up | Checking the logo | All the logos are right | Found as per expectation | N/A | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | Passed
4 |  |  |  | Checkig all the icons | All icons should be present | Found as per expectation | N/A | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | Passed
6 |  |  |  | Veify all the images and background images | All the images should be appeared | Found as per expectation | N/A | Passed
7 |  |  |  | Veify the messagebox | Messagebox should be present | Found as per expectation | N/A | Passed
8 |  |  |  | Verify the footer | Footer should be present | Found as per expectation | N/A | Passed
9 |  |  |  | Checking all the spellings | Should be no spelling mistake | Not found as per expectation | N/A | Passed
10 |  | Functional Testing |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message | N/A | Passed
11 |  |  |  | Checking Full name field is case insensitive | Should accept the provided input | Found as per expectation | AbbCCdd uuXXggDD | Passed
12 |  |  |  | Entering blank at first position in the Full name field | Should not accept the provided input | Found as per expectation | Aakk kkhhQQ | Passed
14 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Not found as per expectation | N/A | Passed
15 |  |  |  | Inputing Fullname with special characters | Should not accept the provided input | found as per expectation | )r55@% **###@%% | Passed
16 |  |  |  | Inputing Full name with numbers | Should not accept the provided input | Not found as per expectation | 64764237856283 | Failed
18 |  |  |  | Inputing full name with alphanumeric characters | Should not accept the provided input | Not found as per expectation | Dhrubo70 abc12 | Failed
19 |  |  |  | Inputing Fullname with alphabets | Should not accept the provided input | Found as per expectation | John Austin | Passed
20 |  |  |  | Entering comma between alphabets for Fullname | Should not accept the provided input | Not found as per expectation | jjs,iioo jjdh,dhu | Failed
21 |  |  |  | Entering space between alphabets for full name | Should accept the provided input | Found as per expectation | Dhruba Nandi abc xrt | Passed
23 |  |  |  | Validating a phone number can only be used one time | Should allow user to register | Found as per expectation | 1871241878 | Passed
24 |  |  |  | Checking by inputing invalid phone number | Should not accept the provided input and display an error message | Found as per expectation with an error message | 436546767 | Passed
26 |  |  |  | Checking verification code | Should accept the provided input | Found as per expectation | 189333 | Passed
27 |  |  |  | Invalid verification code | Should not allow user to register and display a pop message | Found as per expectation | john8888 | Passed
30 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | ty656$12@ | Passed
31 |  |  |  | Inputing different data for password | Should not allow user to register and display a pop message | Found as per expectation | Passworddryb@7686 Confirm password: jnn8888 | Passed
32 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | john@8888 | Passed
|  |  |  | Varify the birthday month | Able to select | Found as per expectation | April | Passed
|  |  |  | Veify the birthday date | Able to select | Found as per expectation | 12 | Passed
|  |  |  | Veify the birthday date | Able to select | Found as per expectation | 2000 | Passed
|  |  |  | Verify the gender | Able to select | Found as per expectation | Male | Passed
46 |  |  |  | Checking 'Sign in with Facebook' | Should allow user to register | Found as per expectation | Click on 'Sign in with Facebook' | Passed
47 |  |  |  | Checking 'Sign in with Google' | Should allow user to register | Found as per expectation | Click on 'Sign in with Google' | Passed
48 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | jane9999 | Passed
49 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | Passed
50 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | Passed
51 |  | Functionality Testing | Login | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | Passed
52 |  |  |  | Checking if the data in password is encrypted | Should be encrypted | Found as per expectation | drb123 | Passed
53 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | gghg@gamil.com | Passed
54 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | dhrua123@gmail.com Password: jane@2222 | Passed
55 |  |  |  | Verifying ‘Reset Your Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | Passed
|  |  |  | Verify slide to continue is working | As per Expectation | Found as per expectation | N/A | Passed
56 |  |  |  | Checking by selecting ‘Reset Your Password’ multiple times | Account should be temporarily restricted and a message should be displayed | Found as per expectation with a message | N/A | Passed
|  |  |  | Vrifying input field without putting Phone Number or Email | A pop up meassage should be shown | Found as per expectation | N/A | Passed
57 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | Passed
|  |  |  | Verify Go Back link is working | As per Expectation | Found as per expectation | N/A | Passed
58 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A | Passed
60 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | Found as per expectation with an error message | Email: drb123@gmail.com Password:drb123 | Passed
61 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation | Email: drb123@gmail.com Password: drb123 | Passed
|  |  |  | Veifying "Register Here" link is working | Should go to Register Page | Found as per expectation | N/A | Passed

## Bug Report
Bug Reporting | Bug Reproting
# SL 01 | #SL 02
Issue:Inputing full name with alphanumeric characters
Issue:Inputing full name with numbers
Reproducing Steps:
Reproducing Steps:
1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the header 3. Fill all the fields with numbers 4.Click 'Sign Up' | 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the header 3. Fill all the fields with alphanumeic character 4.Click 'Sign Up'
Env: Production | Env:Production
Module: Sign Up | Module:Sign Up
Severity: P1 | Sevirity:p1
Responsible QA:Dhruba Nandi | Responsible QA:Dhruba Nandi
Bug Reporting
# SL 03 Issue:Entering comma between alphabets for Fullname 1. Goto the URL https://www.daraz.com.bd/ 2. Click on Register button at the header 3. Fill all the fields with comma between alphabets 4.Click 'Sign Up' Env: Production Module: Sign Up Severity: P1 Responsible QA:Dhruba Nandi

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (49/49)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/49)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (46/49)*100 = 93.88
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (3/49)*100 = 7
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/62)*100 = 0